## Task Table
TASK TABLE
PROJECT TITLE |  |  | COMPANY |  | PROJECT MANAGER |  | DATE
LOSSI - LaBita Online Shopping Site Improvement |  |  | HBL |  | Hana Franklin |  | 2021-10-20
Task Code | Task Name | Predecessor(s) | Optimistic Time | Most Likely Time | Pessimistic Time | PERT - Time Estimates [in days] | Calculated Expected Time [in days]
Shopping Cart Compatability Tasks | [6 empty] | 46
1A | Task 1.1.1 Define Environments | - | 2 | 3 | 4 | 3
1B | Task 1.1.2 Define Requirements | 1A | 2 | 3 | 4 | 3
1C | Task 1.1.3 Define Timelines & targets | 1B | 2 | 3 | 4 | 3
1D | Task 1.2.1 Environment Set-up | 1A | 5 | 5 | 6 | 5.1667
1E | Task 1.2.2 Implement New Features | 1C,1D | 7 | 9 | 11 | 9
1F | Task 1.2.3 Modify Existing Features | 1E | 5 | 7 | 8 | 6.8333
1G | Task 1.3.1 Test | 1F | 7 | 7 | 9 | 7.3333
1H | Task 1.3.2 Report Bugs | 1G | 7 | 7 | 8 | 7.1667
1I | Task 1.3.3 Re-test | 1H | 7 | 7 | 8 | 7.1667
Returns Interface Tasks* | [6 empty] | 47
2A | Task 2.1.1 Verify User Requirements | - | 3 | 4 | 5 | 4
2B | Task 2.1.2 User Flow Design | 2A | 2 | 3 | 4 | 3
2C | Task 2.1.3 Wireframe Creation | 2B | 3 | 4 | 5 | 4
2D | Task 2.1.4 Design Validation | 2C | 1 | 2 | 3 | 2
2E | Task 2.2.1 Environment Set-up | 2A | 7 | 7 | 8 | 7.1667
2F | Task 2.2.2 Implement New Features | 2D,2E | 7 | 8 | 9 | 8
2G | Task 2.2.3 Modify Existing Features | 2F | 7 | 8 | 9 | 8
2H | Task 2.3.1 Test | 2G | 6 | 6 | 7 | 6.1667
2I | Task 2.3.2 Report Bugs | 2H | 6 | 6 | 7 | 6.1667
2J | Task 2.3.3 Re-test | 2I | 6 | 6 | 7 | 6.1667
Color-Blind Friendly Interface Tasks | [6 empty] | 36
3A | Task 3.1.1 Color Design | - | 2 | 3 | 4 | 3
3B | Task 3.1.2 Wireframe Creation | 3A | 5 | 6 | 7 | 6
3C | Task 3.1.3 Design Validation | 3B | 1 | 2 | 3 | 2
3D | Task 3.2.1 Implement New Features | 3C | 7 | 7 | 8 | 7.1667
3E | Task 3.3.1 Test | 3D | 5 | 6 | 7 | 6
3F | Task 3.3.2 Report Bugs | 3E | 5 | 6 | 7 | 6
3G | Task 3.3.3 Re-test | 3F | 5 | 6 | 7 | 6
* Critical path