## Cover Page
Work Breakdown Structure (WBS) and Requirements Traceablity Matrix (RMT) LaBita Online Shopping Site Improvement Project (LOSSI) September 22, 2021 HBL INFORMATION SYSTEMS CONSULTING FIRM OMIS 690 – Information Technology Project Management Bersabel Feleke Abera: Z1888832 Hita Gurunath Kadam: Z1908140 Lauren Wallace: Z1837861

## WBS
WORK BREAKDOWN STRUCTURE DICTIONARY
PROJECT TITLE |  |  | COMPANY | PROJECT MANAGER | DATE
LOSSI - LaBita Online Shopping Site Improvement |  |  | HBL | Hana Franklin | 2021-09-22
WBS Level | WBS Code | Category | Name | Description | Resource(s) | Duration
1 | 1 | Must Have | Shopping Cart Compatibility
2 | 1.1 |  | Planning
3 | 1.1.1 |  | Define Environments | Define devices and operating systems that site shopping cart is expected to work on | Survey Analysis Summary, Project Team | 2 days
3 | 1.1.2 |  | Define Requirements | Define necessary requirements that will be needed by each project member. | Project Team | 2 days
| 1.1.3 |  | Define timelines & targets | Define and construct project timeline that will be met by each team for respective tasks. | Project Team | 2 days
2 | 1.2 |  | Execution
3 | 1.2.1 |  | Environment Set-up | Set up environments and OS for testing with different platforms to check whether application runs well under different configurations | Development Team, Hardware, Software | 5 days
3 | 1.2.2 |  | Implement new features | Code the new features to be incorporated in the application as per project scope. | Development Team, Hardware, Software | 7 days
3 | 1.2.3 |  | Modify existing features | Make essential changes to existing code to meet the new requirements as per project scope. | Development Team, Hardware, Software | 5 days
2 | 1.3 |  | Testing
3 | 1.3.1 |  | Test | Test shopping cart functionality on all defined devices and OS types | Development Team, QA & QC team, Hardware, Software | 7 days
3 | 1.3.2 |  | Report Bugs | Document, report, and resolve any defects | Development Team, QA & QC team | 7 days
3 | 1.3.3 |  | Re-test | Re-test to confirm defect fixes | Development Team, QA & QC team, Hardware, Software | 7 days
1 | 2 | Should Have | Returns Interface
2 | 2.1 |  | Planning
3 | 2.1.1 |  | Verify User Requirements | Confirm user requirements for interface update | Project Team | 3 days
3 | 2.1.2 |  | User Flow Design | Define click-through process of each return action | UX/UI Expert | 2 days
3 | 2.1.3 |  | Wireframe Creation | Create wirefram pages for each part of user flow design | UX/UI Expert | 3 days
3 | 2.1.4 |  | Design Validation | Get final design sign-off | UX/UI Expert, Project Team | 1 day
2 | 2.2 |  | Execution
3 | 2.2.1 |  | Environment Set-up | Set up environments and OS for testing with different platforms to check whether application runs well under different configurations | Development Team, Hardware, Software | 7 days
3 | 2.2.2 |  | Implement new features | Code the new features to be incorporated in the application as per project scope. | Development Team, Hardware, Software | 7 days
3 | 2.2.3 |  | Modify existing features | Make essential changes to existing code to meet the new requirements as per project scope. | Development Team, Hardware, Software | 7 days
2 | 2.3 |  | Testing
3 | 2.3.1 |  | Test | Test returns interface for flow and compatibility | Development Team, QA & QC team, Hardware, Software | 5 days
3 | 2.3.2 |  | Report Bugs | Document, report, and resolve any defects | Development Team, QA & QC team | 5 days
3 | 2.3.3 |  | Re-test | Re-test to confirm defect fixes | Development Team, QA & QC team, Hardware, Software | 5 days
1 | 3 | Could Have | Color-Blind Friendly Interface
2 | 3.1 |  | Planning
3 | 3.1.1 |  | Color Design | Define color-blind friendly schemes to change | UX/UI Expert | 2 days
3 | 3.1.2 |  | Wireframe Creation | Create wireframe for pages that have color scheme changes | UX/UI Expert | 5 days
|  |  | Design Validation | Get final design sign-off | Project Team | 1 day
2 | 3.2 |  | Execution
3 | 3.2.1 |  | Implement new features | Code the new features to be incorporated in the application as per project scope. | Development Team, Hardware, Software | 7 days
2 | 3.3 |  | Testing
3 | 3.3.1 |  | Test | Test coding changes for seamless UI integration | Development Team, QA & QC team, Hardware, Software | 5 days
3 | 3.3.2 |  | Report Bugs | Document, report, and resolve any defects | Development Team, QA & QC team | 5 days
3 | 3.3.3 |  | Re-test | Re-test to confirm defect fixes | Development Team, QA & QC team, Hardware, Software | 5 days

## RTM
REQUIREMENTS TRACEABILITY MATRIX
PROJECT TITLE |  |  | COMPANY | PROJECT MANAGER |  |  | DATE
LOSSI - LaBita Online Shopping Site Improvement |  |  | HBL | Hana Franklin |  |  | 2021-09-22
REQUIREMENT INFORMATION |  |  |  | RELATIONSHIP TRACABILITY
ID | REQUIREMENT | SOURCE | BUSINESS JUSTIFICATION | WBS TASKS DELIVERABLE(S) | TEST STRATEGY | STATUS
REQ-001 | The website needs to be compatible with multiple operating systems | Stephanie Brown Business IT support | Clients will have unlimited access to the online shopping site | 1.1.2 | Test case is developed and used | Pending
REQ-002 | The online shopping cart section is simple and interactive for users to easily navigate through and execute the task in demand. This is especially reflected at the exchange or return function of a purchased item. And, customers are able to undertake this task on a single page. | George Brown Business Finance Manager | Results in excellent user experience and less customer conversion rate | 1.2.2 | A checklist is prepared and functionality test will be applied. | Pending
REQ-003 | Images and graphics elements load quickly without compromising the quality. | Stephanie Brown Business IT support | Smooth and prompt operation of the shopping site satisfies customers. | 1.2.2 | Performance testing | Pending
REQ-004 | Text labels added to color filters of items available for purchase | Esther Brown Business Owner | Accessiblity allowed for color blind customers and inclusiveness bring good reputation of the business | 1.2.2 | A checklist is prepared and functionality test will be applied. | Pending
REQ-005 | The site avoids color combinations that are not color blind friendly. (Avoids color combinations of green-red , green-blue, green-brown, green-black, green-grey, blue-grey, light green-yellow, blue-purple ) | Esther Brown Business Owner | Accessiblity allowed for color blind customers and inclusiveness bring good reputation of the business | 1.2.2 | A checklist is prepared and functionality test will be applied. | Pending
REQ-006 | The online shopping site will use the LaBita business color: Aqua | Esther Brown Business Owner | Consistent and bright appearance of the website. | 1.2.3 | A checklist is prepared and functionality test will be applied. | Pending

## Risk Register
RISK REGISTER
PROJECT TITLE |  |  | COMPANY | PROJECT MANAGER |  |  |  |  | DATE
LOSSI - LaBita Online Shopping Site Improvement |  |  | HBL | Hana Franklin |  |  |  |  | 2021-11-03
Ref ID | Risk Description | Risk Justification/Cause | Risk Category | Probability | Impact | Priority | Owner | Mitigation Action
1 | Project schedule is not clearly defined or understood. | Any change to project schedule causes a change in other critical and competing project constraints. | Project Management Risk | Low | High | 1 | Project Manager | Put scheduling workshops in place with the project team so deliverable timeline is agreed upon and missed deadlines may be reduced.
2 | Unplanned work that must be accommodated. | Scope creep occurence | Project Management Risk | Low | High | 1 | Project Manager | Implement a change control process to control the scope of the project, and/or to communicate additional work to team members.
3 | Project conflicts not resolved in a timely manner. | Disagreements over technical opinions, project priorities, manpower resources, etc. | Project Management Risk | Medium | High | 1 | Project Manager | Hold daily scrum or stand-up meetings to problem-solve conflicts as they occur, in a timely manner.
4 | Added budget/funding requirements | Lack of risk/issues management, estimation errors, unmanaged scope creep, and/or lack of budget accountability | Organizational Risk | Medium | Medium | 2 | IT Steering Committee | Carry out a thorough reference of historical data/lessons learned, leverage company experts and ensure accuracy while creating project budget. Review project progress on a regular basis. Prepare and apply monitoring and controlling mechanisms to track and manage requirement changes.
5 | Poor performance of end-product on interfaces | Graphical user interface doesn't meet specifications | Technical Risk | Medium | High | 1 | IT Lead | Include software interface testing into test cases
6 | Website functionality might be disrupted during the redesign development and transition. | Have negative implication on business revenue. | Technical Risk | Low | High | 1 | Software Developers | Implement these changes during downtime as provided by clients. Keep clients well informed about the duration required and updated status.